## January 2025
Project | Overall RAG status | Funded until | Timeline | [5 empty] | Key issues/risks to be escalated | Request to Board | Mitigations taken | Key Achievements | Links to other documents | Lead(s) | Not yet achieved | Internal links (not for OND Board)
|  |  | Scope | Approve | Set-up | Deliver | Evaluate | Sustain
High Flow (HIU) |  | Mar 25 | [6 empty] | Budget not confirmed beyond March 2025 No agreement as yet on long term funding plan by commissioners or providers. Need confirmation of locality budget | Request to ICB that long-term sustainability proposal as requested by the DIG is provided and if and where HIU sits in the ICB in terms of HIU services co-ordination. Clarification about whether this is to be a commissioned service. | Presented to RDUH Health Inequalities Investment Panel - no confirmed outcome yet. Being re-presented in February. Include in principle in OND funding scenarios. | - Staff recruited & trained & operational - RDUH BI providing ED list monthly - Data collection designed & operational - Exceeding NHSE HIU operational targets - Return on investment calculated at 1:328. For every pound spent, there is a return of £3.28. | Original High Flow Project Review May 24 (for ICB) | Simon Rapsey/David Richardson | - Comms & Engagement plan not in place - Bulk data upload process not yet functioning
High Flow Project Review May 24 (for ICB)
High Flow Project Outline
High Flow Service Specification
Community Flow |  | 2025-03-01 | [6 empty] | - Budget not confirmed beyond March 2025. - Presented at RDUH Investment Panel and approved to be put forward for funding. Need next steps and timescales confirming | Board to agree it's position in terms of continuation of Community Flow if can't be funded by RDUH in 24/25. | Presented at RDUH investment Panl and confirmed that CF will be put forward for funding. | - 420 patients supported since June 2023 - 41.5% reduction in admissions after referral compared to admissions prior to referral - Return on investment calculated at 1:365. For every pound spent, there is a return of £3.65 | https://onenortherndevon.co.uk/wp-content/uploads/2024/07/Community-Flow-2023-2024-Highlight-Report.pdf | Simon Rapsey/Jeff Chinnock/Zoe
Housing Flow pilot |  | 2025-03-01 | [6 empty] | - No funding beyond March 2025 - Low number of referrals |  | Review meeting with NDC being arranged for Jan 25 | The clients being worked with are benefiting from the case worker involvement. |  | Simon Rapsey/Nina
Well Leg Flow |  | 2025-03-01 | [6 empty] | - No funding beyond March 2025 |  | Review meeting with RDUH Lower Limb Therapy Service taken place - unlikely that further funding can be found. Report to be presented at January OND Board meeting. Reports sent to Hannah Tapp. | Positive impact on clients supported and LLTS Team say they value the service. |  | Simon Rapsey
Pain Team Flow |  | Ongoing | [11 empty] | Simon Rapsey/Matt Lund
InHIP Primary Care Outreach |  | Ended | [6 empty] | No commissoned GP outreach service has been commissioned in Northern Devon other than in Barnstaple, which has received funding to continue primary care outreach at the Freedom Centre. | Board to agree whether to fund Belle's Place to continue to support this programme that now has an extension of the clinical input. This was discussed at the last meeting and agreed that the GP outreach element should be part of a commissioning conversation (and the outreach facility to be looked at separately). Confimation needed as to how to progress the primary care element via the ICB. | Board supports the request for equitable provision of primary care outreach services across Northern Devon. • LH linking with converstaions about long term condition management in Trusts • KA exploring any funding opportunities for mitigating for digital exclusion • AB to check whether the data consent for evaluation will allow us to use the ODD to support the business case • AB to confirm from Kristian if the Devon Primary Care Collaborative Board would be the best place to take and if responsibility for commissioning lies with ICB or Public Health | The national InHIP programme were particularly interested in this work and have used it in their national evaluation of the programme. Sarah Williams presented it at the RSGP national conferance. | Health Innovation South West blog about the project | Andrea Beacham/Sarah Williams
InHIP CVD Remote Monitoring |  | Ended | [6 empty] | Business case to RDUH to continue this pilot which has been successful is delayed due to waiting to find out if this can be made interoperable with the patient record system. |  | -Business case going through RDUH operational process |  |  | Andrea Beacham/Poppy/Angie | Business case delayed therefore service has stopped
Poverty Truth Commission |  | 2025-12-01 | [8 empty] | Contacted/met a variety of cross-sector organisations. OND partner staff: North Devon Homes, TDK Lambda, Childrens centre, Petroc, DCC Learn Devon, Wellbeing team Also supported by NDDC, DPT Together. | Sept 26th launch event was successful. 30+ organisations attended to hear testimonies, learn about the PTC and reflect together. Commitments were made Ethics approved for evaluation research Additional funding application success, allowing for additional researcher time (Internal Exeter Uni fund). Steering group reforming to meet needs of project/commission. Commision currently meeting monthly (started Nov 2024) to create shared understanding of poverty/the system, emerging themes will be refined to form priority working groups in Feb/March 2025) | All PTC documents can be found here | James Lander/Andrea Beacham | Logic model/KPIs, Comms plan
Ilfracombe Task Force |  | No funding | [9 empty] | Secretariat established and Programme Leads for key programmes of work. |  | Andrea Beacham/Ken Miles | Delayed due to agreement over governance
Live Longer Better |  | No funding | [6 empty] | Finance to fund licenses for project not secured. Implementation stage £20K needed |  | Collaborator meeting on 19th November . Collaboration with PCN, ICB, Active Devon, RDUHT, Live well braunton/One Communities and LLB platform initiated. Grant application in progress (Fullabrook). Possible collab with RDUHT. Active Devon active participation. HAND governance. PCN IG lead. Living with experts (Platform) providing evaluation / data collection. | LLB HAND 2024.01.17.pdf | Kay Brennan | Decision on what KPIs will be collected. | Live Longer Better – meeting with Darrin Halifax and Tom Mack w/c 14.01.24 to discuss making Devon a LLB committed county. Nothing from Dr Hill on their funding yet from Fullabrook.
FAME |  | Ended - underspend being used until March 25 | [6 empty] | Delivery of FaME across the locality in 2023/4. Evaluation awaited (SR) |  | HAND agreed delivery in 3 places for rest of 24/25 using underspend & remaining PHM funds. SLA complete & being signed off. (JC 8/11) SLA signed off 14/11/24 Academic bid being worked up to focus on rural and coastal communities using teleconferencing delivery of classes Kay meeting with FaME spec leads W/C 12/8 | A FaME course was provided in each of the seven ONE Communities in Northern Devon, 3 new PSIs were trained, 93 people recruited and 66 completed the progrsmme., see evaliation for full report New programme starting in January in Bideford, Barnstaple and Ilfracombe. | fame evaluation | Anita Grigg/ Simon Rapsey/ Jo Curtis
Anticipatory Care PIlots | [8 empty] | Funding from the ICB for the anticipatory care pilot was non-recurrent and no further funding has been found. |  |  | In Torridge Health, from Jan 2023 to end of March 2024; • 42 patients received Anticipatory Care • Medications reviewed in 100% cases In Barnstaple Alliance PCN, from July 2023 to end of March 2024; • 29 patients received Anticipatory Care Dr Fiona Duncan, Sept 2024 • Medications reviewed in 100% cases | Anticipatory Care report for BGS Case Study | Dr Fiona Duncan
One Communities / Community Devlopment (incl. CD&L group and OC group) |  | NDVS/TTVS Lottery funded till Feb 2027, Braunton funded until |  |  |  |  | we have 23/24 OC evaluation and CD evaluation framework (Lottery) | Lottery funded till Feb 2027 | Issue 1: Lack of support for those with mental illness due to link centre closures (Need clarity for Ilfracombe, Holsworthy, Bideford, Barnstaple) Issue 2: OC group Chair due to leave post in March - Require new Chair | 1. Public sector reps needed to work with MH Network 2. Request for replacement board member to chair the One Communities meeting - see Terms of Reference | Link centre # Action - Simon Kitchen will update on judiciary review and implications, locations can contact him direct for clarification. MH drop-ins # DMHA have organised MH drop-ins and peer support groups (Phil Hariss) Intention for ICB and VCSE MH Network # Existing VCSE MH Network (Chaired by Phil) - local networks also exist (e.g MH mycellium in Ilfracombe) # Greg Smith (ICB) - is project managing a ICB led MH partnership to understand MH needs/assets of ND Community (includes Phil Hariss and DPT David Richardson) | OND funded Evaluation partner (Clarity CIC) contracted - engaged key stakeholders of Lottery project and created evaluation framework. 3 new CD posts with NDVS - 2 recruited (C&YP/Lynton & Lynmouth) 1 recruiting (rural & coastal) ND CD Forum setup by NDVS - seeking to align with the OC group to suppport joining up work to reduce duplication. OC group have agenda item to discuss opportunities for joint working amongst different communities / with wider organisations. | Place reports | James Lander/Marie Gould/JW | Updated reporting system (that correlates to evaluation framework)
Job / role description, workplans
CVD Prevention | [11 empty] | - North Devon CVD prevention & Hypertension case finding strategy document close to completion - Pilot of Outreach NHS Health Checks underway, using Freedom Centre & PHM approach for Barnstaple Alliance patients - Productive discussions and agreement with community pharmacy about the use of CP in Hypertension casefinding |  | Oliver Hassall/Kay Brennan | -Stategy document to be finalised -Completion of pilot NHS HC Outreach programmes - Confirmed way of working with community pharmacy as part of wider strategy
Closing the Gap |  | No funding
North Devon CEW Expansion project |  | 2025-03-01 |  | Proposal being developed |  | before March 25

## November 2024
Project | Overall RAG status | Funded until | Timeline | [5 empty] | Key issues/risks to be escalated | Request to Board | Mitigations taken | Key Achievements | Links to other documents | Lead(s) | Not yet achieved | Internal links (not for OND Board)
|  |  | Scope | Approve | Set-up | Deliver | Evaluate | Sustain
High Flow (HIU) |  | Mar 25 | [6 empty] | Budget not confirmed beyond March 2025 No agreement as yet on long term funding plan by commissioners or providers. -New RDUH IG agreement not yet in place with provider |  | - To be discussed at Dec OND board meeting along with all the OND finances for 25/26. - Business case presented to DIG on 3/10 and funding secured from UEC slippage until Mar 25. - Has been raised with RDUH & DPT COOs. - RDUH health inequalities business case process formed. - IG going through RDUH process | - Staff recruited & trained & operational - RDUH BI providing ED list monthly - Data collection designed & operational - Exceeding NHSE HIU operational targets | Original High Flow Project Review May 24 (for ICB) | Simon Rapsey/David Richardson | - Comms & Engagement plan not in place - Bulk data upload process not yet functioning
High Flow Project Review May 24 (for ICB)
High Flow Project Outline
High Flow Service Specification
Community Flow |  | 2024-02-01 | [6 empty] | - Budget not confirmed beyond March 2025. - Reporting process issues not yet resolved. - Unable to meet with RDUH Community Care Group leads due to operational demands. |  | Meeting with RDUH Community leads is being arranged to look at whether Community Flow can be embedded in the Communities Care Group | - Funding secured until 31st March 2025 via successful business case to DIG - - Plans being formulated for sustainability beyond then,likely via RDUH business case - High levels of demand - almost as many referrals in the first 6 months of 24/25 as the whole of 25/26. | https://onenortherndevon.co.uk/wp-content/uploads/2024/07/Community-Flow-2023-2024-Highlight-Report.pdf | Simon Rapsey/Jeff Chinnock/Zoe
Housing Flow pilot |  | 2024-12-01 | [6 empty] | - No funding beyond March 2025 - Low number of referrals |  | Review meeting with NDC being arranged for Nov 24. | The clients being worked with are benefiting from the case worker involvement. |  | Simon Rapsey/Nina
Well Leg Flow |  | 2024-12-01 | [6 empty] | - No funding beyond March 2025 |  | Review meeting with RDUH Lower Limb Therapy Service being arranged for Oct 24. | Positive impact on clients supported and LLTS Team say they value the service. |  | Simon Rapsey
Pain Team Flow |  | Ongoing | [11 empty] | Simon Rapsey/Matt Lund
InHIP Primary Care Outreach |  | Ended | [6 empty] | No commissoned GP outreach service has been commissioned in Northern Devon other than in Barnstaple, which has received funding to continue primary care outreach at the Freedom Centre. |  | Board supports the request for equitable provision of primary care outreach services across Northern Devon. • LH linking with converstaions about long term condition management in Trusts • KA exploring any funding opportunities for mitigating for digital exclusion • AB to check whether the data consent for evaluation will allow us to use the ODD to support the business case • AB to confirm from Kristian if the Devon Primary Care Collaborative Board would be the best place to take and if responsibility for commissioning lies with ICB or Public Health |  | Health Innovation South West blog about the project | Andrea Beacham/Sarah Williams
InHIP CVD Remote Monitoring |  | Ended | [6 empty] | Business case to RDUH to continue this pilot which has been successful is delayed due to delay in receiving the necessary information for the business case. |  | -Business case going through RDUH operational process |  |  | Andrea Beacham/Poppy/Angie | Business case delayed therefore service has stopped
Poverty Truth Commission |  | 2025-12-01 | [6 empty] | Community Commissioner recruitment is an issue. Need 2-5 more. (open to all 18+ but ideally would meet the demographic need: 70+yrs, minority ethnic background or under 18-25yrs. | Help with recruiting 2-5 more Community Commissioners, ideally from the unrepresented groups (over 70, under 24, minority ethnic). Please book James in to speak with staff members who could recruit commissioners from Ilfracombe. | Contacted/met a variety of cross-sector organisations. OND partner staff: North Devon Homes, TDK Lambda, Childrens centre, Petroc, DCC Learn Devon, Wellbeing team Also supported by NDDC, DPT Together. | Sept 26th launch event was successful. 30+ organisations attended to hear testimonies, learn about the PTC and reflect together. Commitments were made Commision started Nov 21st. 8 (of 10) Community Commisioners and 6 (of 12) attended 1st session. Ethics approved for evaluation research Additional funding application success, allowing for additional researcher time (Internal Exeter Uni fund). Steering group reforming to meet needs of project/commission. | All PTC documents can be found here | James Lander/Andrea Beacham | Logic model/KPIs, Comms plan
Ilfracombe Task Force |  | No funding | [6 empty] | Some of the strategic leadership on the OI board has been lost when board directors moved over to the OND board |  |  |  |  | Andrea Beacham/Ken Miles | Delayed due to agreement over governance
Live Longer Better |  | No funding | [6 empty] | Finance to fund licenses for project not secured. Implementation stage £20K needed | Consider supporting funding - key outcomes from other areas who have piloted is reduced sedentary behaviour in older adults and improved QOL. | Collaborator meeting on 19th November . Collaboration with PCN, ICB, Active Devon, RDUHT, Live well braunton/One Communities and LLB platform initiated. Grant application in progress (Fullabrook). Possible collab with RDUHT. Active Devon active participation. HAND governance. PCN IG lead. Living with experts (Platform) providing evaluation / data collection. | LLB HAND 2024.01.17.pdf | Kay Brennan | Decision on what KPIs will be collected.
FAME |  | Ended - underspend being used until March 25 | [6 empty] | Delivery of FaME across the locality in 2023/4. Evaluation awaited (SR) |  | HAND agreed delivery in 3 places for rest of 24/25 using underspend & remaining PHM funds. SLA complete & being signed off. (JC 8/11) SLA signed off 14/11/24 Academic bid being worked up to focus on rural and coastal communities using teleconferencing delivery of classes Kay meeting with FaME spec leads W/C 12/8 | A FaME course was provided in each of the seven ONE Communities in Northern Devon, 3 new PSIs were trained, 93 people recruited and 66 completed the progrsmme., see evaliation for full report | fame evaluation | Anita Grigg/ Simon Rapsey/ Jo Curtis
One Communities / Community Devlopment | [6 empty] | we have 23/24 evaluation | Lottery funded till Feb 2027 | Issue: Lack of support for those with mental illness due to link centre closures (Need clarity for Ilfracombe, Holsworthy, Bideford, Barnstaple) | Public sector reps needed to work with MH Network (chaired by Phil Hariss) | Simon Kitchen will update of judiciary review and implications, locations can contact him direct for clarification. DMHA have organised MH drop-ins and peer support groups (Phil Hariss) MH Network (Chaired by Phil) are discussing responses - local networks also exist (e.g MH mycellium in Ilfracombe) | OND funded Evaluation partner (Clarity CIC) contracted - currently undertaking stakeholder engagament. 3 new CD posts with NDVS - 2 recruited (C&YP/Lynton & Lynmouth) 1 recruiting (rural & coastal) ND CD Forum setup by NDVS - seeking to align with the OC group. | Place reports | James Lander/Marie Gould/JW | Evaluation framework
Job / role description, workplans
CVD Prevention | [11 empty] | - North Devon CVD prevention & Hypertension case finding strategy document close to completion - Pilot of Outreach NHS Health Checks underway, using Freedom Centre & PHM approach for Barnstaple Alliance patients - Productive discussions and agreement with community pharmacy about the use of CP in Hypertension casefinding |  | Oliver Hassall/Kay Brennan | -Stategy document to be finalised -Completion of pilot NHS HC Outreach programmes - Confirmed way of working with community pharmacy as part of wider strategy
New OND HI Strategy |  | No funding
North Devon CEW Expansion project |  | 2025-03-01 |  | Proposal being developed |  | before March 25

## October 2024
Project | Overall RAG status | Funded until | Timeline | [5 empty] | Key issues/risks to be escalated | Request to Board | Mitigations taken | Key Achievements | Links to other documents | Lead(s) | Not yet achieved | Internal links (not for OND Board)
|  |  | Scope | Approve | Set-up | Deliver | Evaluate | Sustain
High Flow (HIU) |  | Mar 25 | [6 empty] | Budget not confirmed beyond March 2025 No agreement as yet on long term funding plan by commissioners or providers. -New RDUH IG agreement not yet in place with provider |  | - To be discussed at Dec OND board meeting along with all the OND finances for 25/26. - Business case presented to DIG on 3/10 and funding secured from UEC slippage until Mar 25. - Has been raised with RDUH & DPT COOs. - RDUH health inequalities business case process formed. - IG going through RDUH process | - Staff recruited & trained & operational - RDUH BI providing ED list monthly - Data collection designed & operational - Exceeding NHSE HIU operational targets | Original High Flow Project Review May 24 (for ICB) | Simon Rapsey/David Richardson | - Comms & Engagement plan not in place - Bulk data upload process not yet functioning
High Flow Project Review May 24 (for ICB)
High Flow Project Outline
High Flow Service Specification
Community Flow |  | 2024-02-01 | [6 empty] | - Budget not confirmed beyond March 2025. - Reporting process issues not yet resolved. - Unable to meet with RDUH Community Care Group leads due to operational demands. |  | Meeting with RDUH Community leads is being arranged to look at whether Community Flow can be embedded in the Communities Care Group | - Funding secured until 31st March 2025 via successful business case to DIG - - Plans being formulated for sustainability beyond then,likely via RDUH business case - High levels of demand - almost as many referrals in the first 6 months of 24/25 as the whole of 25/26. | https://onenortherndevon.co.uk/wp-content/uploads/2024/07/Community-Flow-2023-2024-Highlight-Report.pdf | Simon Rapsey/Jeff Chinnock/Zoe
Housing Flow pilot |  | 2024-12-01 | [6 empty] | - No funding beyond March 2025 - Low number of referrals |  | Review meeting with NDC being arranged for Nov 24. | The clients being worked with are benefiting from the case worker involvement. |  | Simon Rapsey/Nina
Well Leg Flow |  | 2024-12-01 | [6 empty] | - No funding beyond March 2025 |  | Review meeting with RDUH Lower Limb Therapy Service being arranged for Oct 24. | Positive impact on clients supported and LLTS Team say they value the service. |  | Simon Rapsey
Pain Team Flow |  | Ongoing | [11 empty] | Simon Rapsey/Matt Lund
InHIP Primary Care Outreach |  | Ended | [6 empty] | No commissoned GP outreach service has been commissioned in Northern Devon other than in Barnstaple, which has received funding to continue primary care outreach at the Freedom Centre. |  | Board supports the request for equitable provision of primary care outreach services across Northern Devon. • LH linking with converstaions about long term condition management in Trusts • KA exploring any funding opportunities for mitigating for digital exclusion • AB to check whether the data consent for evaluation will allow us to use the ODD to support the business case • AB to confirm from Kristian if the Devon Primary Care Collaborative Board would be the best place to take and if responsibility for commissioning lies with ICB or Public Health |  | Health Innovation South West blog about the project | Andrea Beacham/Sarah Williams
InHIP CVD Remote Monitoring |  | Ended | [6 empty] | Business case to RDUH to continue this pilot which has been successful is delayed due to delay in receiving the necessary information for the business case. |  | -Business case going through RDUH operational process |  |  | Andrea Beacham/Poppy/Angie | Business case delayed therefore service has stopped
Poverty Truth Commission |  | 2025-12-01 | [6 empty] | Community Commissioner recruitment is an issue. Need 4-7 more. Demographic need: community commissioners 70+yrs, minority ethnic background or under 25yrs. | Help with recruiting 4-7 more Community Commissioners, ideally from the unrepresented groups (over 70, under 24, minority ethnic). Please book James in to speak with staff members who could recruit commissioners from Ilfracombe. | Contacted/met a variety of cross-sector organisations. OND partner staff: North Devon Homes, TDK Lambda, Childrens centre, Petroc, DCC Learn Devon, Wellbeing team Also supported by NDDC, DPT Together. | Sept 26th launch event was successful. 30+ organisations attended to hear testimonies, learn about the PTC and reflect together. Commitments were made and the civic/organisational leaders will be recruited/confirmed in Oct 2024. The Commission will begin asap once commissioners have been agreed. | All PTC documents can be found here | James Lander/Andrea Beacham | Logic model/KPIs
Ilfracombe Task Force |  | No funding | [6 empty] | Some of the strategic leadership on the OI board has been lost when board directors moved over to the OND board |  |  |  |  | Andrea Beacham/Ken Miles | Delayed due to agreement over governance
Live Longer Better |  | No funding | [6 empty] | Finance to fund licenses for project not secured. Implementation stage £20K needed | Consider supporting funding - key outcomes from other areas who have piloted is reduced sedentary behaviour in older adults and improved QOL. | Collaboration with PCN, ICB, Active Devon, RDUHT, Live well braunton/One Communities and LLB platform initiated. Grant application in progress (Fullabrook). Possible collab with RDUHT. Active Devon active participation. HAND governance. PCN IG lead. Living with experts (Platform) providing evaluation / data collection. | LLB HAND 2024.01.17.pdf | Kay Brennan | Decision on what KPIs will be collected.
FAME |  | Ended - underspend being used until March 25 | [6 empty] | Delivery of FaME across the locality in 2023/4. Evaluation awaited (SR) |  | HAND agreed delivery in 3 places for rest of 24/25 using underspend & remaining PHM funds. SLA being finalised. (JC) Academic bid being worked up to focus on rural and coastal communities using teleconferencing delivery of classes Kay meeting with FaME spec leads W/C 12/8 | A FaME course was provided in each of the seven ONE Communities in Northern Devon, 3 new PSIs were trained, 93 people recruited and 66 completed the progrsmme., see evaliation for full report | fame evaluation | Anita Grigg/ Simon Rapsey/ Jo Curtis
One Communities / Community Devlopment | [6 empty] | we have 23/24 evaluation | Lottery funded till Feb 2027 | Issue: Lack of support for those with mental illness due to link centre closures (Need clarity for Ilfracombe, Holsworthy, Bideford, Barnstaple) | Issue: Require DCC update for clarity of avaialble support for those with mental illness (due to lack of delivery of promised services - pathways for individuals from link centre, 3xweekly drop-ins, DCC-led peer support group (DMHA have supported VCSE to set up a fortnightly drop-in at Salvation Army & this is the only provision - as reported by Community Developers in Ilfracombe & Holsworthy) Risk: One Ilfracombe unaware of who/where link centre users are (so are unable to offer support) | External evaluator (tbc - October 2024) | New CD workplans in place (NDVS/TTVS), Reporting mechanism in place that links with National occupational standards | Place reports | James Lander/Marie Gould/JW | Evaluation framework
Job / role description, workplans
CVD Prevention | [11 empty] | - North Devon CVD prevention & Hypertension case finding strategy document close to completion - Pilot of Outreach NHS Health Checks underway, using Freedom Centre & PHM approach for Barnstaple Alliance patients - Productive discussions and agreement with community pharmacy about the use of CP in Hypertension casefinding |  | Oliver Hassall/Kay Brennan | -Stategy document to be finalised -Completion of pilot NHS HC Outreach programmes - Confirmed way of working with community pharmacy as part of wider strategy
New OND HI Strategy |  | No funding
North Devon CEW Expansion project |  | 2025-03-01 |  | Proposal being developed |  | before March 25

## September 2024
Project | Overall RAG status | Funded until | Timeline | [5 empty] | Key issues/risks to be escalated | Request to Board | Mitigations taken | Key Achievements | Links to other documents | Lead(s) | Not yet achieved | Internal links (not for OND Board)
|  |  | Scope | Approve | Set-up | Deliver | Evaluate | Sustain
High Flow (HIU) |  | Oct 2024 | [6 empty] | Budget not confirmed beyond October 24 -New RDUH IG agreement not yet in place with provider | To advise the route/s for applying for winter funds To advise of any other potential funding sources | - Raised with ICB & asked to submit interim report to Antony Fitzgerald to be submitted by 23/08. - Raised at LCP Programme Group & advised winter pressure monies may be available - however have been advised plans/allocation not yet made - Raised with NHSE via Lynne Dickson - Regional Lead who has included as a risk in the National Highlight Report - IG going through RDUH process | - Staff recruited & trained & operational - RDUH BI providing ED list monthly - Data collection designed & operational - Exceeding NHSE HIU operational targets | Original High Flow Project Review May 24 (for ICB) | Simon Rapsey/David Richardson | - Comms & Engagement plan not in place - Quarterly reporting format not yet agreed - Bulk data upload process not yet functioning
High Flow Project Review May 24 (for ICB)
High Flow 1st report – Jan-Mar 24
High Flow Project Outline
High Flow Service Specification
Draft Reporting Template
Community Flow |  | 2024-02-01 | [9 empty] | Funding secured until 31st March 2025 via successful business case to DIG - - Plans being formulated for sustainability beyond then,likely via RDUH business case - Started to use the same data recording process as HIU - full quarterly reprt due July | https://onenortherndevon.co.uk/wp-content/uploads/2024/07/Community-Flow-2023-2024-Highlight-Report.pdf | Simon Rapsey/Jeff Chinnock/Zoe
Housing Flow pilot |  | 2024-12-01 | [9 empty] | Pilot very slow to become operational due to internal staffing/capacity issues within NDC. - Worker now operational & recieving referrals -Full quarterly report due in July |  | Simon Rapsey/Nina
Well Leg Flow |  | 2024-12-01 | [9 empty] | After a slow start the project is going well, referrals recieved & patients supported. - Full quarterly report due beginning of July -LLTS Team very pleased with early patient outcomes |  | Simon Rapsey
Pain Team Flow |  | Ongoing | [11 empty] | Simon Rapsey/Matt Lund
InHIP Primary Care Outreach |  | Ended | [6 empty] | No commissoned GP outreach service has been commissioned in Northern Devon other than in Barnstaple, which has received funding to continue primary care outreach at the Freedom Centre. | Request that the Board supports the request for equitable provision of primary care outreach services. Request that the board identifies where within the system we can take this request. |  |  | Health Innovation South West blog about the project | Andrea Beacham/Sarah Williams
InHIP CVD Remote Monitoring |  | Ended | [6 empty] | Business case to RDUH to continue this pilot which has been successful is delayed due to delay in receiving the necessary information for the business case. |  | -Business case going through RDUH operational process |  |  | Andrea Beacham/Poppy/Angie | Business case delayed therefore service has stopped
Poverty Truth Commission |  | 2025-12-01 | [6 empty] | Community Commissioner recruitment is an issue. We started with 12 and now have 9, with 1 more at risk due to housing. (2 have left the group due to choice, 1 from relocation due to eviction). Demographic need: community commissioners 70+yrs, minority ethnic background or under 25yrs. | Help with recruiting up to 6 more Community Commissioners, ideally from the unrepresented groups (over 70, under 24, minority ethnic). Please book James in to speak with staff members who could recruit commissioners from Ilfracombe. | Contacted/met a variety of cross-sector organisations. OND partner staff: North Devon Homes, TDK Lambda, Childrens centre, Petroc, DCC Learn Devon, Wellbeing team Also supported by NDDC, DPT Together. | Recruited Community commissioners and supporting them to share at launch event (Sept 2024) Cross-sector steering group incl. lived experience Lots of in-kind partner support has been offered: Town Council: free space; Exeter Uni: reflection sessions; DHMA councelling support for participants; ICB: monthly supervision; Landmark Theatre: facilitation support for commissioner story-telling; Church Action on Poverty: media training Evaluation funding (OND/DCC) and partners secured (Exeter University/Devon Communities Foundation) Co-created agenda for launch event on Sept 26th 2024 | All PTC documents can be found here | James Lander/Andrea Beacham | Learning Log not yet set up KPIs not yet in logic model
Ilfracombe Task Force |  | No funding | [6 empty] | Some of the strategic leadership on the OI board has been lost when board directors moved over to the OND board | That OND members have an increased role and attendance at the OI meetings while there is a specific focus on Ilfracombe's inequalities (further info from Ken Miles at board meeting) |  |  |  | Andrea Beacham/Ken Miles | Delayed due to agreement over governance
Live Longer Better |  | No funding | PCN LTC citizen activation | [5 empty] | Finance to fund licenses for project not secured. Implementation stage £20K needed | Consider supporting funding - key outcomes from other areas who have piloted is reduced sedentary behaviour in older adults and improved QOL. | Collaboration with PCN, ICB, Active Devon, RDUHT, Live well braunton/One Communities and LLB platform initiated. Grant application in progress (Fullabrook). Possible collab with RDUHT. Active Devon active participation. HAND governance. PCN IG lead. Living with experts (Platform) providing evaluation / data collection. | LLB HAND 2024.01.17.pdf | Kay Brennan | Decision on what KPIs will be collected.
FAME |  | Ended | [6 empty] | Delivery of FaME across the locality in 2023/4. Evaluation awaited (SR) |  | 3 options for delivery for rest of 24/25 using underspend & remaining PHM funds worked up by Anita and Jo Curtis. Has been discussed by HAND on 18/9 (JC) Academic bid being worked up to focus on rural and coastal communities using teleconferencing delivery of classes Kay meeting with FaME spec leads W/C 12/8 | A FaME course was provided in each of the seven ONE Communities in Northern Devon, 3 new PSIs were trained, 93 people recruited and 66 completed the progrsmme., see evaliation for full report | fame evaluation | Anita Grigg/ Simon Rapsey/ Jo Curtis
One Communities | [6 empty] | we have 23/24 evaluation | Lottery funded till Feb 2027 | Issue: Lack of support for those with mental illness due to link centre closures (Need clarity for Ilfracombe, Holsworthy, Bideford, Barnstaple) | Issue: Require DCC update for clarity of avaialble support for those with mental illness (due to lack of delivery of promised services - pathways for individuals from the link centre, 3xweekly drop-ins, DCC-led peer support group (DMHA have supported VCSE to set up a fortnightly drop-in at Salvation Army and this is the only provision) (as reported by Community Developers in Ilfracombe & Holsworthy) Risk: One Ilfracombe unaware of who / where the link centre users are (so are unable to offer available support) | External evaluator (tbc - September 2024) |  | Place reports | James Lander/Marie Gould/JW | Evaluation framework, new CD workplans (NDVS), CD portfolio of evidence (CD NOS)
Job / role description, workplans
CVD Prevention | [11 empty] | - North Devon CVD prevention & Hypertension case finding strategy document close to completion - Pilot of Outreach NHS Health Checks underway, using the Freedom Centre and a PHM approach for Barnstaple Alliance patients - Productive discussions and agreement with community pharmacy about the use of CP in Hypertension casefinding |  | Oliver Hassall/Kay Brennan | -Stategy document to be finalised -Completion of pilot NHS HC Outreach programmes - Confirmed way of working with community pharmacy as part of wider strategy
New OND HI Strategy |  | No funding
North Devon CEW Expansion project |  | 2025-03-01 |  | Proposal being developed |  | before March 25

## August 2024
Project | Overall RAG status | Funded until | Timeline | [5 empty] | Key issues/risks to be escalated | Request to Board | Mitigations taken | Key Achievements | Links to other documents | Lead(s) | Not yet achieved | Internal links (not for OND Board)
|  |  | Scope | Approve | Set-up | Deliver | Evaluate | Sustain
High Flow (HIU) |  | Oct 2024 | [6 empty] | Budget not confirmed beyond October 24 -New RDUH IG agreement not yet in place with provider | To advise the route/s for applying for winter funds To advise of any other potential funding sources | - Raised with ICB & asked to submit interim report to Antony Fitzgerald to be submitted by 23/08. - Raised at LCP Programme Group & advised winter pressure monies may be available - however have been advised plans/allocation not yet made - Raised with NHSE via Lynne Dickson - Regional Lead who has included as a risk in the National Highlight Report - IG going through RDUH process | - Staff recruited & trained & operational - RDUH BI providing ED list monthly - Data collection designed & operational - Exceeding NHSE HIU operational targets | Original High Flow Project Review May 24 (for ICB) | Simon Rapsey/David Richardson | - Comms & Engagement plan not in place - Quarterly reporting format not yet agreed - Bulk data upload process not yet functioning
High Flow Project Review May 24 (for ICB)
High Flow 1st report – Jan-Mar 24
High Flow Project Outline
High Flow Service Specification
Draft Reporting Template
Community Flow |  | 2024-02-01 | [9 empty] | Funding secured until 31st March 2025 via successful business case to DIG - - Plans being formulated for sustainability beyond then,likely via RDUH business case - Started to use the same data recording process as HIU - full quarterly reprt due July | https://onenortherndevon.co.uk/wp-content/uploads/2024/07/Community-Flow-2023-2024-Highlight-Report.pdf | Simon Rapsey/Jeff Chinnock/Zoe
Housing Flow pilot |  | 2024-12-01 | [9 empty] | Pilot very slow to become operational due to internal staffing/capacity issues within NDC. - Worker now operational & recieving referrals -Full quarterly report due in July |  | Simon Rapsey/Nina
Well Leg Flow |  | 2024-12-01 | [9 empty] | After a slow start the project is going well, referrals recieved & patients supported. - Full quarterly report due beginning of July -LLTS Team very pleased with early patient outcomes |  | Simon Rapsey
Pain Team Flow |  | Ongoing | [11 empty] | Simon Rapsey/Matt Lund
InHIP Primary Care Outreach |  | Ended | [6 empty] | No commissoned GP outreach service has been commissioned in Northern Devon other than in Barnstaple, which has received funding to continue primary care outreach at the Freedom Centre. | Request that the Board supports the request for equitable provision of primary care outreach services. Request that the board identifies where within the system we can take this request. |  |  | Health Innovation South West blog about the project | Andrea Beacham/Sarah Williams
InHIP CVD Remote Monitoring |  | Ended | [6 empty] | Business case to RDUH to continue this pilot which has been successful is delayed due to delay in receiving the necessary information for the business case. |  | -Business case going through RDUH operational process |  |  | Andrea Beacham/Poppy/Angie | Business case delayed therefore service has stopped
Poverty Truth Commission |  | 2025-12-01 | [6 empty] | Community Commissioner recruitment is an issue. We had 12, 2 have left the group due to choice, 1 from relocation due to eviction). We also don't have any community commissioners over 70, of an minority ethnic background or under the age of 24. | Help with recruiting up to 6 more Community Commissioners, ideally from the unrepresented groups (over 70, under 24, minority ethnic). Please confirm at 2.07.24 board meeting if you are willing to book James in to speak with staff members who could recruit commissioners from Ilfracombe. |  | Lots of in-kind partner support has been offered: Town Council: free space; Exeter Uni: reflection sessions; DHMA councelling support for participants; ICB: monthly supervision; Landmark Theatre: facilitation support for commissioner story-telling; Church Action on Poverty: media training Co-created agenda for launch event | All PTC documents can be found here | James Lander/Andrea Beacham | Learning Log not yet set up KPIs not yet in logic model
Ilfracombe Task Force |  | No funding | [6 empty] | Some of the strategic leadership on the OI board has been lost when board directors moved over to the OND board | That OND members have an increased role and attendance at the OI meetings while there is a specific focus on Ilfracombe's inequalities (further info from Ken Miles at board meeting) |  |  |  | Andrea Beacham/Ken Miles | Delayed due to agreement over governance
Live Longer Better |  | No funding | PCN LTC citizen activation | [5 empty] | Finance to fund licenses for project not secured. Implementation stage £20K needed | Consider supporting funding - key outcomes from other areas who have piloted is reduced sedentary behaviour in older adults and improved QOL. | Collaboration with PCN, ICB, Active Devon, RDUHT, Live well braunton/One Communities and LLB platform initiated. Grant application in progress (Fullabrook). Possible collab with RDUHT. Active Devon active participation. HAND governance. PCN IG lead. Living with experts (Platform) providing evaluation / data collection. | LLB HAND 2024.01.17.pdf | Kay Brennan | Decision on what KPIs will be collected.
FAME |  | Ended | [6 empty] | Delivery of FaME across the locality in 2023/4. Evaluation awaited (SR) |  | Academic bid being worked up to focus on rural and coastal communities using teleconferencing delivery of classes Kay meeting with FaME spec leads W/C 12/8 | Funding opportunities - The Dunhill Medical Trust | Simon Rapsey / Kay Brennan
One Communities | [6 empty] | we have 23/24 evaluation | Lottery funded till Feb 2027 | / | / |  | CVS partners secured Lottery funding, ICB match funding CD employers/line managers in place LWIB self-funded, BTC has employed OB CD 7 x volunteer Chairs Key findings from external evaluation - One Communities demonstrates considerable effort to take a person-centred (particularly through co production) and a partnership working approach / clear positive outcomes stemming from these approaches​ incl. connectedness​, skill sharing​, empowerment​, wellbeing outcomes​, confidence​ & combating loneliness & isolation | Place reports | James Lander/Marie Gould/JW | Evaluation framework, new CD workplans (NDVS), CD portfolio of evidence (CD NOS)
Job / role description, workplans
CVD Prevention | [11 empty] | - North Devon CVD prevention & Hypertension case finding strategy document close to completion - Pilot of Outreach NHS Health Checks underway, using the Freedom Centre and a PHM approach for Barnstaple Alliance patients - Productive discussions and agreement with community pharmacy about the use of CP in Hypertension casefinding |  | Oliver Hassall/Kay Brennan | -Stategy document to be finalised -Completion of pilot NHS HC Outreach programmes - Confirmed way of working with community pharmacy as part of wider strategy
New OND HI Strategy |  | No funding

## July 2024
Project | Overall RAG status | Funded until | Timeline | [5 empty] | Key issues/risks to be escalated | Request to Board | Key Achievements | Links to other documents | Lead(s) | Not yet achieved | Internal links (not for OND Board)
|  |  | Scope | Approve | Set-up | Deliver | Evaluate | Sustain
High Flow (HIU) |  | Oct 2024 | [6 empty] | Budget not confirmed beyond October 24 -New RDUH IG agreement not yet in place with provider | To advise the route/s for applying for winter funds To advise of any other potential funding sources | - Staff recruited & trained & operational - RDUH BI providing ED list monthly - Data collection designed & operational - Exceeding NHSE HIU operational targets | Original High Flow Project Review May 24 (for ICB) | Simon Rapsey/David Richardson | - Comms & Engagement plan not in place - Quarterly reporting format not yet agreed - Bulk data upload process not yet functioning
High Flow Project Review May 24 (for ICB)
High Flow 1st report – Jan-Mar 24
High Flow Project Outline
High Flow Service Specification
Draft Reporting Template
Community Flow |  | 2024-02-01 | [8 empty] | Funding secured until 31st March 2025 via successful business case to DIG - - Plans being formulated for sustainability beyond then, most likely via a internal RDUH business case - Started to us the same data recording process as HIU - full quarterly reprt due in July | https://onenortherndevon.co.uk/wp-content/uploads/2024/07/Community-Flow-2023-2024-Highlight-Report.pdf | Simon Rapsey/Zoe/Lyndsey?
Housing Flow pilot |  | 2024-12-01 | [8 empty] | Pilot very slow to become operational due to internal staffing/capacity issues within NDC. - Worker now operational and recieving referrals -Full quarterly report due in July |  | Simon Rapsey/Nina
Well Leg Flow |  | 2024-12-01 | [8 empty] | After a slow start the project is going well, referrals recieved and patients recieving support. - Full quarterly report due beginning of July -LLTS Team very pleased with early patient outcomes |  | Simon Rapsey/?
Pain Team Flow |  | Ongoing | [10 empty] | Simon Rapsey/Matt Lund
InHIP Primary Care Outreach |  | Ended | [10 empty] | Andrea Beacham/Sarah Williams
InHIP CVD Remote Monitoring |  | Ended | [10 empty] | Andrea Beacham/Poppy/Angie | Business case delayed therefore service has stopped
Poverty Truth Commission |  | 2025-12-01 | [6 empty] | Community Commissioner recruitment is an issue. We had 12, 2 have left the group due to choice, 1 from relocation due to eviction). We also don't have any community commissioners over 70, of an minority ethnic background or under the age of 24. | Help with recruiting up to 6 more Community Commissioners, ideally from the unrepresented groups (over 70, under 24, minority ethnic). Please confirm at 2.07.24 board meeting if you are willing to book James in to speak with staff members who could recruit commissioners from Ilfracombe. | Lots of in-kind partner support has been offered: Town Council: free space; Exeter Uni: reflection sessions; DHMA councelling support for participants; ICB: monthly supervision; Landmark Theatre: facilitation support for commissioner story-telling; Church Action on Poverty: media training Co-created agenda for launch event | All PTC documents can be found here | James Lander/Andrea Beacham | Learning Log not yet set up KPIs not yet in logic model
Ilfracombe Task Force |  | No funding | [6 empty] | Some of the strategic leadership on the OI board has been lost when board directors moved over to the OND board | That OND members have an increased role and attendance at the OI meetings while there is a specific focus on Ilfracombe's inequalities (further info from Ken Miles at board meeting) |  |  | Andrea Beacham/Ken Miles | Delayed due to agreement over governance
Live Longer Better |  | No funding | [10 empty] | Kay Brennan
FAME |  | Ended | [6 empty] | Awaiting Devon-wide plan |  |  |  | Simon Rapsey
One Communities | [6 empty] | we have 23/24 evaluation | Lottery funded till Feb 2027 | / | / | CVS partners secured Lottery funding, ICB match funding CD employers/line managers in place LWIB self-funded, BTC have employed OB CD 7 volunteer Chairs Key findings from external evaluation - One Communities demonstrates considerable effort to take a person-centred (particularly through co production) and a partnership working approach / A number of clear positive outcomes stemming from these approaches​ incl. connectedness​, skill sharing​, empowerment​, wellbeing outcomes​, confidence​ and combating loneliness and isolation | Place reports | James Lander/Marie Gould/JW | Evaluation framework, new CD workplans (NDVS), CD portfolio of evidence (CD NOS)
Job / role description, workplans
CVD Prevention | [12 empty] | Oliver Hassall/Kay Brennan
New OND HI Strategy |  | No funding | [7 empty] | Confirmation of approach proposed by HI Group

## June 2024
|  | Overall RAG status | Timeline | [5 empty] | Key issues/risks |  | Overall RAG status | Timeline | [5 empty] | Key issues/risks
|  |  | Scope | Approve | Set-up | Delivery | Evaluate | Sustainability |  |  |  | Scope | Approve | Set-up | Delivery | Evaluate | Sustainability
|  | Green = some areas may be amber but no significant risk to project delivery Amber = multiple areas of issue or risk to project delivery Red = significant risk to project delivery | Discover stage (double diamond) | Project initiation proposal: Theory of Change Logic Model Budget confirmation Assurance process | Project Governance Finance Plan IG agreements Service Specification Procurement Comms & Engagement plan Evaluation plan Recruitment & Training | Project output delivery Process monitoring Data collection (outputs & outcomes & other metrics) Learning Log Monitoring & reporting | Final evaluation report measured against the Evaluation Framework | What is the plan for continuing the established of the project? Who will manage? Who will pay? | Main reasons for the amber or red RAG status |  | Green = some areas may be amber but no significant risk to project delivery Amber = multiple areas of issue or risk to project delivery Red = significant risk to project delivery | Discover stage (double diamond) | Project initiation proposal: Theory of Change Logic Model Budget confirmation Assurance process | Project Governance Finance Plan IG agreements Service Specification Procurement Comms & Engagement plan Evaluation plan Recruitment & Training | Project output delivery Process monitoring Data collection (outputs & outcomes & other metrics) Learning Log Monitoring & reporting | Final evaluation report measured against the Evaluation Framework | What is the plan for continuing the established of the project? Who will manage? Who will pay? | Main reasons for the amber or red RAG status
Project | Overall RAG status | Funded until | Timeline | [5 empty] | Key issues/risks to be escalated | Request to Board | Key Achievements | Links to other documents | Lead(s) | Not yet achieved | Internal links (not for OND Board)
|  |  | Scope | Approve | Set-up | Deliver | Evaluate | Sustain
High Flow (HIU) |  | Oct 2024 | [6 empty] | Budget not confirmed beyond October 24 -New RDUH IG agreement not yet in place with provider | To advise the route/s for applying for winter funds To advise of any other potential funding sources | - Staff recruited & trained & operational - RDUH BI providing ED list monthly - Data collection designed & operational - Exceeding NHSE HIU operational targets | Original High Flow Project Review May 24 (for ICB) | Simon Rapsey/David Richardson | - Comms & Engagement plan not in place - Quarterly reporting format not yet agreed - Bulk data upload process not yet functioning
High Flow Project Review May 24 (for ICB)
High Flow 1st report – Jan-Mar 24
High Flow Project Outline
High Flow Service Specification
Draft Reporting Template
Community Flow |  | 2024-02-01 | [8 empty] | Funding secured until 31st March 2025 via successful business case to DIG - - Plans being formulated for sustainability beyond then, most likely via a internal RDUH business case - Started to us the same data recording process as HIU - full quarterly reprt due in July | https://onenortherndevon.co.uk/wp-content/uploads/2024/07/Community-Flow-2023-2024-Highlight-Report.pdf | Simon Rapsey/Zoe/Lyndsey?
Housing Flow pilot |  | 2024-12-01 | [8 empty] | Pilot very slow to become operational due to internal staffing/capacity issues within NDC. - Worker now operational and recieving referrals -Full quarterly report due in July |  | Simon Rapsey/Nina
Well Leg Flow |  | 2024-12-01 | [8 empty] | After a slow start the project is going well, referrals recieved and patients recieving support. - Full quarterly report due beginning of July -LLTS Team very pleased with early patient outcomes |  | Simon Rapsey/?
Pain Team Flow |  | Ongoing | [10 empty] | Simon Rapsey/Matt Lund
InHIP Primary Care Outreach |  | Ended | [10 empty] | Andrea Beacham/Sarah Williams
InHIP CVD Remote Monitoring |  | Ended | [10 empty] | Andrea Beacham/Poppy/Angie | Business case delayed therefore service has stopped
Poverty Truth Commission |  | 2025-12-01 |  | Theory of change & logic model in development, budget confirmed | Aim to finalise by September 2024 | Delivery plan, monitoring & reporting in development | External evaluation partner secured | 3 month 'embed' phase to explore whats next | Community Commissioner recruitment is an issue. We had 12, 2 have left the group due to choice, 1 from relocation due to eviction and 1 due to relocate for improved housing (8 remaining). Diversity could be improved: Ideally recruit 70+, minority ethnic background and under the age of 25. | Help with recruiting up to 7 more Community Commissioners, ideally from the unrepresented groups (over 70, under 24, minority ethnic). Please confirm if you are able to directly recruit and/or are willing to book James in to speak with staff members who could help directly recruit commissioners from Ilfracombe. | Lots of in-kind partner support has been offered: Town Council: free space; Exeter Uni: reflection sessions; Exeter Uni/Devon Communities Foundation collaborative evaluation; DHMA councelling support for participants; ICB: monthly supervision; Landmark Theatre: facilitation support for commissioner story-telling; Church Action on Poverty: media training Co-created agenda for launch event | All PTC documents can be found here | James Lander/Andrea Beacham | Learning Log not yet set up KPIs not yet in logic model
Ilfracombe Task Force |  | No funding | [6 empty] | Some of the strategic leadership on the OI board has been lost when board directors moved over to the OND board | That OND members have an increased role and attendance at the OI meetings while there is a specific focus on Ilfracombe's inequalities (further info from Ken Miles at board meeting) |  |  | Andrea Beacham/Ken Miles | Delayed due to agreement over governance
Live Longer Better |  | No funding | PCN LTC citizen activation | Implementation stage £20K needed | Grant application in progress (Fullabrook). Possible collab with RDUHT. Active Devon active participation. HAND governance. PCN IG lead | Living with experts (Platform) providing evaluation / data collection. |  | PCN health and wellbeing team delivery. | Finance to fund licenses for project not secured. | Consider supporting funding - key outcomes from other areas who have piloted is reduced sedentary behaviour in older adults and improved QOL. | Collaboration with PCN, ICB, Active Devon, RDUHT, Live well braunton/One Communities and LLB platform initiated. | LLB HAND 2024.01.17.pdf | Kay Brennan | Decision on what KPIs will be collected.
Anticipatory Care Pilots | [12 empty] | ?
FAME |  | Ended | Academic bid being worked up to focus on rural and coastal communities using teleconferencing delivery of classes | Undisclosed at present from Univeristy of Manchester | Kay meeting with FaME spec leads W/C 12/8 |  |  |  | Awaiting Devon-wide plan |  | delivery of FaME across the locality in 2023/4. Evaluation awaited (SR) | Funding opportunities - The Dunhill Medical Trust | Simon Rapsey / Kay Brennan
One Communities |  |  |  | Theory of change & logic model in development, budget confirmed | Aim to finalise by September 2024 | Delivery plan, monitoring & reporting in development | Seeking external evaluation partner | Lottery funded till Feb 2027 | / | / | CVS partners secured Lottery funding, ICB match funding CD employers/line managers in place LWIB self-funded, BTC have employed OB CD 7 volunteer Chairs Key findings from external evaluation - One Communities demonstrates considerable effort to take a person-centred (particularly through co production) and a partnership working approach / A number of clear positive outcomes stemming from these approaches​ incl. connectedness​, skill sharing​, empowerment​, wellbeing outcomes​, confidence​ and combating loneliness and isolation | Place reports | James Lander/Marie Gould/JW | Evaluation framework, new CD workplans (NDVS), CD portfolio of evidence (CD NOS)
CVD Prevention | [12 empty] | Oliver Hassall/Kay Brennan
New OND HI Strategy |  | No funding | [7 empty] | Confirmation of approach proposed by HI Group

## Instructions
Overall RAG status | Timeline | [5 empty] | Key issues/risks | Not yet achieved | Key Achievements | Key Milestones | Lead(s) | Links to other documents
| Scope | Approve | Set-up | Delivery | Evaluate | Sustainability | [5 empty] | Links to other documents
Green = some areas may be amber but no significant risk to project delivery Amber = multiple areas of issue or risk to project delivery Red = significant risk to project delivery | Discover stage (double diamond) | Project initiation proposal: Theory of Change Logic Model Budget confirmation Assurance process | Project Governance Finance Plan IG agreements Service Specification Procurement Comms & Engagement plan Evaluation plan Recruitment & Training | Project output delivery Process monitoring Data collection (outputs & outcomes & other metrics) Monitoring & reporting | Final evaluation report measured against the Evaluation Framework | What is the plan for continuing the established of the project? Who will manage? Who will pay? | Main reasons for the amber or red RAG status

## Development Groups
1. HAND (meets every 2 months)
Developing the partnership group’s membership, TOR and priorities
Live, Longer, Better PCN project and Active Devon CoP - northern coastal PCN/ RDUHT
FaME / Falls prevention in the community
UEC ICS strategic / priority overlap/common purpose
Development of Integrated Care Co-ordination hubs (RDUHT led)
EHCH – led by Dr Duncan
Hospital at home - led by RDUHT Hannah Hopkins
Dementia Care/support
2. THIPA (meets every 2 months)
Developing a strategy
Place based partnership alignment with Sport England/Active Devon
SMI and Physical Activity knowledge and skills toolkit delivery - on hold
3. Healthy Weight, Physical Activity and Movement Partnership (bi yearly)
Developing the Partnership group’s membership and TOR – supported by ICB
Active Hospital Pilot incorporating waiting well (led by RDUHT)
Active travel forum (meets every 6 weeks) – stakeholder for Joint local plan and Transport Plans. Increasing bikeability delivery across ND. Developing active travel CoP for local organisations.
4. OND Strategy (every 2 weeks)
Workplace Wellness conference developing with DWP and SWBC
5. H.I (monthly)
CVD Prevention project (northern Devon and ICS wide)
Healthy Learning labs Devon (ICB led) – approaches to reducing complications of excess weight - await next steps
Devon Healthy weight steering group (CYP focused)
Children's CEW service development
6. One Communities
OC priority plans linking with Community development
7. Community development and learning
Lottery funded CD offer
JFP priorities

## test
Project |  |  | Timeline | [5 empty] | RAG status (Achieving Targets) | RAG status (Risks/Issues) | Red/Amber RAG comments | Green RAG comments (achievements this month) |  |  | Key Milestones | Lead(s)
ONE NORTHERN DEVON |  |  | Scope | Approve | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 3 |  |  |  |  | Evaluate | Exit/ Continuation agreement
High Flow | [10 empty] | Delays due to IG, Contracting & finalising reporting Funding ends Oct 2024 |  |  | HIU partners who benefit agree to continue to pay for the service | Milestone 1: Project set-up documents completed - Milestone 2: Q1 X Patients onboarded Q1 X Patients discharged | Simon Rapsey/David Richardson
Community Flow | [15 empty] | Simon Rapsey/Zoe/Lyndsey?
Housing Flow pilot | [15 empty] | Simon Rapsey/Nina
Well Leg Flow | [15 empty] | Simon Rapsey/?
Pain Team Flow | [15 empty] | Simon Rapsey/Matt Lund
InHIP Primary Care Outreach | [15 empty] | Andrea Beacham/Sarah Williams
InHIP CVD Remote Monitoring | [10 empty] | Business case delayed therefore service has stopped |  |  |  |  | Andrea Beacham/Poppy/Angie
Poverty Truth Commission | [15 empty] | James Lander/Andrea Beacham
Ilfracombe Task Force | [10 empty] | Delayed due to agreement over governance |  |  |  |  | Andrea Beacham/Ken Miles
Live Longer Better | [15 empty] | Kay Brennan
Anticipatory Care Pilots | [15 empty] | ?
FAME | [15 empty] | Simon Rapsey
One Communities | [15 empty] | James Lander/Marie Gould/JW
CVD Prevention | [15 empty] | Oliver Hassall/Kay Brennan
New OND HI Strategy
Project | Overall RAG status (within all tolerance) | Funded until | Timeline | [5 empty] | Reasons for RAG status | (Risks/Issues) |  | Key acheivements | Issues & Risk Description |  | Key Milestones | Lead(s) | Links to other documents
ONE NORTHERN DEVON |  |  | Scope | Approve | Set-up | Delivery | Evaluate | Sustainability Plan
|  |  | Discover stage (double diamond) | Project initiation proposal: Theory of Change Logic Model Budget confirmation Assurance process | Project Governance Finance Plan IG agreements Service Specification Procurement Comms & Engagement plan Evaluation plan Recruitment & Training | Project output delivery Process monitoring Data collection (outputs & outcomes & other metrics) Monitoring & reporting | Final evaluation report measured against the Evaluation Framework | What is the plan for continuing the established of the project? Who will manage? Who will pay?
High Flow (HIU) | [8 empty] | .- Budget not confirmed beyond October 24 .- RDUH agreement not yet in place with provider .- Comms & Engagement plan not in place .- Quarterly reporting format not yet agreed .- Bulk data upload process not functioning |  | Delays due to IG, Contracting & finalising reporting Funding ends Oct 2024 | .-Data collection .- .-Exceeding targets . . |  |  | Milestone 1: Project set-up documents completed - Milestone 2: Q1 X Patients onboarded Q1 X Patients discharged | Simon Rapsey/David Richardson | Project Action Log Project Initiation Document Quarterly Highlight Report Website Link Theory of Change Logic Model Process Map Double Diamond
Community Flow | [15 empty] | Simon Rapsey/Zoe/Lyndsey?
Housing Flow pilot | [15 empty] | Simon Rapsey/Nina
Well Leg Flow | [15 empty] | Simon Rapsey/?
Pain Team Flow | [15 empty] | Simon Rapsey/Matt Lund
InHIP Primary Care Outreach | [15 empty] | Andrea Beacham/Sarah Williams
InHIP CVD Remote Monitoring | [10 empty] | Business case delayed therefore service has stopped |  |  |  |  | Andrea Beacham/Poppy/Angie
Poverty Truth Commission | [15 empty] | James Lander/Andrea Beacham
Ilfracombe Task Force | [10 empty] | Delayed due to agreement over governance |  |  |  |  | Andrea Beacham/Ken Miles
Live Longer Better | [15 empty] | Kay Brennan
Anticipatory Care Pilots | [15 empty] | ?
FAME | [15 empty] | Simon Rapsey
One Communities | [15 empty] | James Lander/Marie Gould/JW
CVD Prevention | [15 empty] | Oliver Hassall/Kay Brennan
New OND HI Strategy
Project |  |  | Timeline | [11 empty] | RAG status (On Time) | RAG status (Achieving Targets) | RAG status (Risks/Issues) | Red/Amber RAG comments | Green RAG comments (achievements this month) | What is still needed | Key Milestones | Lead(s)
ONE NORTHERN DEVON |  |  | Scope | Approve | Milestone 1 Target | Milestone 2 Target | Milestone 3 | Milestone 4 |  |  |  |  | Evaluate | Exit/ Continuation agreement
High Flow |  |  |  |  | *Project set-up documents completed *Processes agreed & staff trained | Q1 Delivery: X Patients onboarded, X Patients discharged | Q2 Delivery: X Patients onboarded, X Patients discharged | Q3 Delivery: X Patients onbarded, X Patients discharged | [5 empty] | HIU partners who benefit agree to continue to pay for the service |  |  |  | Delays due to IG, Contracting & finalising reporting Funding ends Oct 2024 |  |  | Milestone 1: *Project set-up documents completed *Processes agreed & staff trained Milestone 2: Q1 Delivery: X Patients onboarded, X Patients discharged Milestone 3: Q2 Delivery: X Patients onboarded, X Patients discharged Milestone 4: Q3 Delivery: X Patients onbarded, X Patients discharged | Simon Rapsey/David Richardson
Community Flow | [21 empty] | Simon Rapsey/Zoe/Lyndsey?
Housing Flow pilot | [21 empty] | Simon Rapsey/Nina
Well Leg Flow | [21 empty] | Simon Rapsey/?
Pain Team Flow | [21 empty] | Simon Rapsey/Matt Lund
InHIP Primary Care Outreach | [21 empty] | Andrea Beacham/Sarah Williams
InHIP CVD Remote Monitoring | [17 empty] | Business case delayed therefore service has stopped |  |  |  | Andrea Beacham/Poppy/Angie
Poverty Truth Commission | [21 empty] | James Lander/Andrea Beacham
Ilfracombe Task Force | [17 empty] | Delayed due to agreement over governance |  |  |  | Andrea Beacham/Ken Miles
Live Longer Better | [21 empty] | Kay Brennan
Anticipatory Care Pilots | [21 empty] | ?
FAME | [21 empty] | Simon Rapsey
One Communities | [21 empty] | James Lander/Marie Gould/JW
CVD Prevention | [21 empty] | Oliver Hassall/Kay Brennan
New OND HI Strategy