## Action log
Completed | Action | Responsible | Due date | Notes
| Agree to continue with Lottery bid as a No1 priority | MG/ST
| Set CD&L meeting to monthly | JL |  | JL emailed Isobel to change meeting settings on 19/10/23
| Drive CD&L within Northern Devon Futures H&W / Communities group | AB / MG |  | Marie & Andrea agreed to help align
| Secure independant Chair | KB |  | John Womersley agreed to be Chair
| Admin support | JL |  | No ICB support available, members of group to create action log only
| Request direction from ICB (Darin Halifax) incl. do we have permission to change/edit objectives (more meaningful to group members) | JL/JW |  | JW/AB/JL met with Darin on 15/2
| Confirm an OND LCP executive lead for this group | AB |  | Andrea Beacham
| Invite councils (all levels) | JL |  | Town and District Councils, that responded, added to membership
| Invite Active Devon to join CD&L group | JL
| Align with NDF communities and Place group | JL / MG |  | Met on July 23rd (see note)
| CD&L group to create recommendation(s) for ways of working upwards to ICB, OND LCP & NDF e.g. to reduce meeting/work duplication | JW
| John to pickup Laptop from NDVS | AB |  | NDVS are loaning John a laptop
| Aligning with ELCP (Jeff Chinnock to join July meeting to discuss with members) | JL/JC |  | Booked to attend 2-7-24
| Isobel to send a Doodle poll to group members to reschedule next meeting due | Isobel
| OND LCP to confirm match funding in writing to NDVS for Lottery fund release | AB
| Terms of Reference - Take out item 9, add ‘we report to programme board’ | JW |  | See NLCP CD&L steering group – draft Jan 2024
| (Sept 2024) what is important to Communities & potential funders (Look back at past engagement data) | JL |  | See emerging themes
| (Sept 2024) Baseline - what have we learned to date? (Exeter evaluation) | AB |  | See summary in June Place report
| Doodle Poll for Extended ‘Day out’ CD&L group session - what we are working towards (our aims) | AB / Isobel | 2025-01-01 | Wed 29/01/2025 09:00 - 17:00 Community Learning and Development Group Away Day
| Book venue for 'day out' session | LF
| Discuss focusing on inequality for the 20% most deprived with OC group | JL |  | For current CD initiatives - Collect their postcode / vulnerable group type. OND are working with partners to understand how they target deprived populations / vulnerable groups
2025-03-18 | Need new Chair for OC group | JL/LF | 2025-04-01
2025-03-18 | Secure secretariat support | MG | 2025-04-01
2025-03-18 | Invite relevant strategic NDF members to the CD&L group | MG | 2025-04-01
2025-04-15 | Meeting Rescheduling: Forward the invite for the 20th of May to Izzy, for 1400-1600, at Queen's House. (Marie) | MG | 2025-05-01
2025-04-15 | Invite List Update: Send a list of the people being invited to the next meeting to Marie for verification. (Izzy) | IV | 2025-05-01
2025-04-15 | Agenda Update: Update the agenda for the next meeting to include a section for a tactical plan discussion. (Marie) | MG | 2025-05-01
2025-04-15 | Strategy Day Workshop: Suggest to Pete that the strategy day includes a workshop on the sustainability plan for strong communities. (Marie) | MG | 2025-05-01
2025-05-20 | Circulate current OND and NDF structure diagrams | DS | 2025-06-01
2025-05-20 | Group to review membership (append mailing list to Minutes) | All/DS | 2025-06-01
2025-05-20 | Strategy Day Workshop: Andrea to take agreed priority list | AB | 2025-05-01
2025-05-20 | Align place report under strategic headings | JL | 2025-06-01
| Potential investor engagement: Enquiry with businesses re: private sector investment & support (inviting businesses to engagement events). | MG/LF | ongoing | NDVS Business breakfast 5th - potential to attend centremanager@greenlanes.co.uk Craig's email
2025-04-15 | Potential investor engagement: Create a potential investor engagement plan to identify investors' priorities. (James) | JL | 2025-05-01
2025-03-18 | JL to discuss with Marie/Beki/Andrea - to repurpose JL/external evaluators time to make sure the impact measure/management work happens | JL/MG/BS/AB | 2025-04-02
2025-05-20 | Share updated governance overview OND/NDF plan with CD&L group members
Note on E9: JL to see 'Joint Forward Plan - Community Development' email for replies NDC - (Ken) could involve our economic (Place) team, customer services or Bev in Member Services. We will have a discussion and I’ll let you know.Ken will let us know Bideford TC - Paul Swan (Clerk), Cllr Cllr Ken Hind (James Craigie as substitute) Ilfracombe TC - Terry Elliot tbc

## Risk-Issue log
# | Risk / Issue | Area | Risk/Issue | Impact | (Potential) Mitigations (Action log number) | Success
1 | Risk | CD&L group | Non-Lottery funded partners being left out | Lack collaborative efforts | Invite employers and leads to stategic CD&L group
2 | Issue | Governance | Confusion over governance and wider objectives | Hard to understand how to most effectively build community voice into regional governance structures | Adjust governance doc to reflect our current understanding Ask all CDs/OCs if this makes sense
3 | Risk | Operational | Employer directing (rather than supporting) CD work | Community priorities and actions are superseeded | - CDs tasked to gather local priorities to shape their workplan - Lottery funding is testing CDNOS as a framework to create shared understanding and manage/align CD work
5 | Issue | Governance | Too many meetings (project, local) | Duplication of effort | Merger of strategic regional groups (OND & NDF) Marie to invite the NDF Communities members to the CD&L group
6 | Risk | Insight | We don't know who the OC members are | We do not know if OCs are representative or whos missing | CD Employers to request member lists and hold centrally to reduce risk if staff/volunteer absent CDs to collect demographic data
7 | Issue | Funding | LWIB Lottery funding ends in Oct 2025 | No funding for Community Development officer role (x1) | Invite LWIB to CD&L group
9 | Issue | Operational | CDs face competing local demands | CDs report feeling overwhelmed and then make non-evidence-based decisions | Requires an agreed process that supports CDs to say ‘No’ to demands that are not aligned with priorities. Finding ways to empower residents to do the work themselves (rather than expect CD to do everything)
10 | Risk | Relationships | Some CDs have poor/no links with key support service staff (practitioners e.g Social prescriber, Community health teams). | Risk to collaborative infrastructure Priorities are not informed by needs identified by service staff | System leader support required (to meet service managers) to allow CDs to focus on building local relationships with service staff
11 | Risk | Investment | Potential investor requests may skew local priorities | Local community priorities will be ignored | - Agree guiding paradigm-shift we are working towards - how do investors view 'community power' and working with rather than to via and asset-based, collaborative approach - Survey (NDC software) / focus groups with private & public sector investors (to determine outputs, outcomes & benefits expected)
12 | Risk | Learning | Lottery evaluation learning not yet being shared outside of Lottery | Reduces ability to learn, improve and ensure evaluation is what partners need | Implement feedback loops: Learning to be shared with CVS', OND, NDF, OCs, CDs (via steering groups / place report / CD/OC forums)
13 | Issue | Funding | Currently funders are not promoting collaboration | Money is spread thinly and across multiple strategies/approaches (e.g. Lottery funded biosphere £0.5M and TTVS/NDVS £0.5M) | DCF/T are given public sector money to manage - This model be used to ‘promote’ collaborative bidding
14 | Issue | Impact | No agreed Impact measurement & management. CD work is hard to map to impact software | Hard to communicate impact with potential investors | Determine outputs, outcomes and benefits investor would require to invest OND/DeVA have access to impact reporting software - Meet with Impact Reporting / Social Value Engine to determine potential measures